## Functionality
Functional Requirements Source
PMP
BRD / HLBRD
IP | Project Name | Directorate | Requirement | Functionality Met? (Y/N) | Scope Risks/Issues/ Comments
346a | Food Modernization | FD | Architecture: Web-application should be accessible over the internet and have a single-user log-in to access all functions | YES | N/A
346a | Food Modernization | FD | Product Identifier: The application will create a unique identifier for each record. | YES | N/A
346a | Food Modernization | FD | Product Tombstone Information: The application will allow tombstone data about a product to be imported or entered manually. Ability to cross link “same product” (e.g. brand name A of product B, however UPC code has changed from 2009 because the net quantity of package has changed) – this might not be an importing feature, maybe within the database somewhere when checking data??? | YES | N/A
346a | Food Modernization | FD | Product Packaging Information: Package information for each UPC of a product (i.e. Label data) can be imported or added for each product in the database. | YES | N/A
346a | Food Modernization | FD | Product Sales Information: Sales information can be imported or manually added for each product UPC in the database | YES | N/A
346a | Food Modernization | FD | Validation of Mandatory Fields: When creating new products, packaging or sales records, mandatory input fields must be indicated to the user by a visual indicator (e.g.: an ‘*’ asterisk within the field label). An error message must occur if any mandatory value is not met. The Error Message must be a descriptive message describing the field(s) values that are failing validation. | YES | N/A
346a | Food Modernization | FD | Validation of Business Rules: A business rule is defined as embedded logic that compare one field value against other field values or ranges of acceptable values. Business rule validation should occur upon when creating or editing records. An error message must occur if any business rule or mandatory value is not met. The Error Message must be a descriptive message describing the field(s) values that are failing validation. | YES | N/A
346a | Food Modernization | FD | Product List View: There should be a list view of all products in the database. The list can be sorted by any column and should be filterable (i.e. by “Creation Date”) This view should visually indicate any missing mandatory data. The columns of each row should be editable in place. Each product record should be “selectable” and will take the user to the view/entry form for the selected product. | NO | N/A
346a | Food Modernization | FD | Product Packaging List View: There should be a list view of all product packaging records in the database. The list can be sorted by any column and should be filterable (i.e. by “Creation Date”). This view should visually indicate any missing mandatory data. The columns in each row should be editable in place. Each product package record should be “selectable” and will take the user to the view/entry form for the product record of the selected package record. The original package record should be highlighted to facilitate finding the row in cases when there are many rows. | NO | N/A
346a | Food Modernization | FD | Product Sales List View: There should be a list view of all product sales records in the database. The list can be sorted by any column and should be filterable (i.e. by “Creation Date”). This view should visually indicate any missing mandatory data. Each Sales record should be “selectable” and will take the user to the view/entry form for the product record of the selected sales record. The original sales record should be highlighted to facilitate finding the row in cases when there are many rows. | NO | N/A
346a | Food Modernization | FD | Usability: Ability of fields to have pre-defined list of accepted values, ability to view list, point and click these values. | YES | N/A
346a | Food Modernization | FD | Usability: Ability to “make visible” or “hide” columns in lists, modify their size or change their order using mouse clicks and drag-and-drop. | YES | N/A
346a | Food Modernization | FD | Reporting: Ability to create reports on product attributes? | YES | N/A
346a | Food Modernization | FD | XML naming-convention: The XML file naming convention must conform to the Health Canada standard naming convention (TBD) | YES | N/A
346a | Food Modernization | FD | XML Data Standard (Future): The XML file must align to the HL7 SLP data standards to ensure interoperability | YES | N/A
346a | Food Modernization | FD | Importing: The ability to import Product Tombstone, Packaging and/or Sales Data should be possible from .XML or .XLS formatted files | YES | N/A
346a | Food Modernization | FD | Retain Imported Data: All data imported through the import mechanism must be retained for data quality and auditing purposes | YES | N/A
346a | Food Modernization | FD | Data Quality: Data being imported should be able to be reviewed for quality before being written to the database. | YES | N/A
346a | Food Modernization | FD | Data Consistency: The ability to highlight inconsistent data (missing or incorrect UPC codes or data fields), data outliers etc… | YES | N/A
346a | Food Modernization | FD | History and Auditing: Data imported should be tagged with the date of importation and its source. | YES | N/A
346a | Food Modernization | FD | User Access: A single user type will be created that has access to all functions. | YES | N/A
346a | Food Modernization | FD | Security Designation for REP information: The information within the REP templates will contain sensitive information. Therefore, the information being sent shall be deemed Protected B. The transfer, management and communications of the REP information shall conform to the Government of Canada Protected B policy and procedures. | YES | N/A
346a | Food Modernization | FD | Standards: The application will follow or comply with the following standards. 1. Ability to extract XML v1.0 – The W3C extensible markup language standard 2. Supports GoC Web Content Accessibility Guidelines (WET 4 Compliant). | YES | N/A
400 | Common Submission Intake | RMOD | Implement Common Tracking System (CTS) | YES | N/A
400 | Common Submission Intake | RMOD | Implement Regulatory Enrolment Process (REP) | YES | N/A
400 | Common Submission Intake | RMOD | Implement Automated validation and loading of submissions | YES | N/A
400 | Common Submission Intake | RMOD | Increase usage of Common Subm. Repository and viewer | YES | N/A
400 | Common Submission Intake | RMOD | Increase usage of Common Electronic Services Gateway | YES | N/A
|  |  | Centralize resources toward Subm. Intake organization | YES | N/A
400 | Common Submission Intake | RMOD | Migration to RPS format across product lines | YES | N/A
618 | Modernization of Canada Vigilance | MHPD | Upgrade ARISg/ESM and Electronic Submission Module (ESM) software to be compliant with the latest pharmacovigilance data standards (ICSR and E2B R3). | YES | N/A
618 | Modernization of Canada Vigilance | MHPD | Leverage the administrative benefits of the latest version of the ARISg/ESM software (e.g., reduces the amount of administrative effort and technical support needed to maintain the system on a day to day basis). | YES | N/A
618 | Modernization of Canada Vigilance | MHPD | Implement Aris Global’s Intake and Triage (I&T) software; a complementary add-on software module to ARISg that will help automate the processing of non-standard AR reports (before and after mandatory reporting comes into effect). | YES | N/A
450 | Drug and Health Product Register R.2 | RMOD | Technical Implementation Guidance | YES | N/A
450 | Drug and Health Product Register R.2 | RMOD | Schema | YES | N/A
450 | Drug and Health Product Register R.2 | RMOD | 2004 Style sheets for all five PM templates (Standard, NOCC, Subsequent Entry Product, Schedule C and Schedule D) | YES | N/A
450 | Drug and Health Product Register R.2 | RMOD | 2016 Style sheets for all five PM templates (Standard, NOCC, Subsequent Entry Product, Schedule C and Schedule D) | YES | N/A
450 | Drug and Health Product Register R.2 | RMOD | Online validation application with encoded technical and business rules | YES | N/A
450 | Drug and Health Product Register R.2 | RMOD | OID Catalogue Database (containing OIDs, codes and terms related to the product monograph) | YES | N/A
450 | Drug and Health Product Register R.2 | RMOD | DHPR Website: The technical capability to receive, validate, process, store and publish SPM’s | YES | N/A
450 | Drug and Health Product Register R.2 | RMOD | DHPR Website: Publish API’s for the following: LNHPD, MDALL, DPD Online, NOC, CT Online, Summary Reports | YES | N/A
450 | Drug and Health Product Register R.2 | RMOD | DHPR Website: Partial E2B compliance for XML output from voluntary adverse event reporting form | YES | N/A
501 | NNHPD IT Renewal | ONPP | Deployment of the new Amendment and Notifications Tool (A&N) | YES | N/A
501 | NNHPD IT Renewal | ONPP | Deployment of a web-based electronic Product Licence Application (ePLA) | YES | N/A
501 | NNHPD IT Renewal | ONPP | Development of an object model for validation | YES | N/A
501 | NNHPD IT Renewal | ONPP | Normalize monograph data for validation | YES | N/A
501 | NNHPD IT Renewal | ONPP | Deployment of a web-based data validation model in conjunction with ePLA | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Capture Requests and Follow-Ups from Practitioners | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Capture Attached Documents With Request | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Data Entry of Drugs Forms A, B, C, and the Medical Devices special access request form | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Capture Requests and Follow-Ups from Practitioners | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Capture Attached Documents With Request | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Data Entry of Drugs Forms A, B, C, and the Medical Devices special access request form | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Import Faxed Forms | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Communications Tracking | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Link or Attach Drug / Medical Devices Product Documents | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Registration for Secure Data Transmission (to and from Health Canada) | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Ability for SAP Clients to access the system via mobile device | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Bilingual User Interface | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Single interface for drugs/medical devices | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Automatic Workflow | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Modify Workflow | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Automatic Letter Generation | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | View Request Status Capability | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Secure Transport In/Out – Requests, additional information and Follow-up | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Storage of Original Incoming Requests | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Storage of Outgoing Letters/Notices | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Storage of Request and Drug/ medical device Histories | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Storage of Incoming Follow-ups | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Storage of Drug and medical device Product Documents | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Storage of External User Registrations | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Integration with GCDOCS (or other HC IM initiative) | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Full Search and Retrieve Capabilities | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Full Drug and Medical Device Details | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Remote Access to the System | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Wireless Mobile Device Access | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Data Migration | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Data Transmissions - Protected B | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | Data Storage – Protected B | YES | N/A
603 | Special Access Program Modernization (eSAP) | TPD | On-Line User Guide | YES | N/A
601 | Revision of Canada's Food Guide | ONPP | The development of a CFG Style Guide that will be applied to present Canada’s Food Guide healthy eating recommendations and resources with a consistent look and feel | YES | N/A
601 | Revision of Canada's Food Guide | ONPP | The design of the CFG visual for Canadians that clearly articulates Health Canada’s healthy eating information | YES | N/A
601 | Revision of Canada's Food Guide | ONPP | The design, development, deployment and support of the CFG Web Portal that will be an integrated user-centric experience through a responsive web design that allows Canadians and stakeholders to obtain CFG related information. | YES | N/A
601 | Revision of Canada's Food Guide | ONPP | Hosting services for the CFG Online Platform will be provided through the Government of Canada unclassified public cloud services contracting vehicle. | YES | N/A
602 | Structured Regulatory Documents | RMOD | Open access to all Product Monographs and all versions of product monograph | YES | N/A
602 | Structured Regulatory Documents | RMOD | XML Documents: Product Monograph, CPID, Notice of Compliance, Level III Change, Controlled Vocabulary | YES | N/A
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | WP 1: PRCI Public interface Public Interface | YES | N/A
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | WP 2: Search Tool | YES | N/A
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | WP 3: Public Storage and Repository | YES | N/A
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | WP 4: Interfaces and Infrastructure | YES | N/A
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | WP 5: Internal Work Tracking Module | YES | N/A
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | WP 6: De-Identification Tool - that enable the process of | YES | N/A
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | WP 7: Web Analytics and Reporting | YES | N/A
634 | Medical Device Post-Market System Renewal | MHPD | Publication and/or revision of guidance related to post-market medical device reporting | YES | N/A
634 | Medical Device Post-Market System Renewal | MHPD | Develop an electronic and web-based submission intake mechanism that uses industry standards for data collection and information exchange | YES | N/A
634 | Medical Device Post-Market System Renewal | MHPD | Post-market medical device report collection and manual entry when provided outside an electronic/web-based process | YES | N/A
634 | Medical Device Post-Market System Renewal | MHPD | Post-market medical device reporting workflow management across all groups in the medical device program – Ensure alignment with pre-market and post-market through data architecture, where appropriate | YES | N/A
634 | Medical Device Post-Market System Renewal | MHPD | Post-market medical device report evaluation - Enable proactive data driven analytical decision support | YES | N/A
634 | Medical Device Post-Market System Renewal | MHPD | Post-market medical device report disclosure and publication of decisions (consistent with HC’s Regulatory Transparency and Openness Framework); | YES | N/A
634 | Medical Device Post-Market System Renewal | MHPD | Address changes based on regulatory updates, as needed. | YES | N/A
703 | Data Analytics Tool | MHPD | TBD | YES | N/A
703 | Data Analytics Tool | MHPD | TBD | YES | N/A
703 | Data Analytics Tool | MHPD | TBD | YES | N/A
Note on A5: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A6: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A7: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A8: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A9: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A10: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A11: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A12: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A13: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A14: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A15: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A16: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A17: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A18: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A19: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A20: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A21: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A22: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A23: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A24: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A25: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A26: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A27: Sarah-Emily Carle: Source: BRD, Gate 3, v3 Date: 2016-05-30 EC-FIPT Approved
Note on A35: Sarah-Emily Carle: Source: Section 2.1.1 scope definition in PMP
Note on A36: Sarah-Emily Carle: Source: Section 2.1.1 scope definition in PMP
Note on A37: Sarah-Emily Carle: Source: Section 2.1.1 scope definition in PMP
Note on A38: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A39: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A40: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A41: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A42: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A43: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A44: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A45: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A46: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A47: Sarah-Emily Carle: Source: PMP section 2.1.1
Note on A48: Sarah-Emily Carle: Source: PMP section 2.1.1
Note on A49: Sarah-Emily Carle: Source: PMP section 2.1.1
Note on A50: Sarah-Emily Carle: Source: PMP section 2.1.1
Note on A51: Sarah-Emily Carle: Source: PMP section 2.1.1
Note on A52: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A53: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A54: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A55: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A56: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A57: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A58: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A59: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A60: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A61: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A62: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A63: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A64: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A65: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A66: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A67: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A68: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A69: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A70: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A71: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A72: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A73: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A74: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A75: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A76: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A77: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A78: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A79: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A80: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A81: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A82: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A83: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on A84: Sarah-Emily Carle: Source: Gate 2 HLBRD
Note on D85: Sarah-Emily Carle: Source: Charter scope boundaries section 2.3.3
Note on D86: Sarah-Emily Carle: Source: Charter scope boundaries section 2.3.3
Note on D87: Sarah-Emily Carle: Source: Charter scope boundaries section 2.3.3
Note on D88: Sarah-Emily Carle: Source: Charter scope boundaries section 2.3.3
Note on D89: Sarah-Emily Carle: Source: Approved Gate 1 Deck
Note on D90: Sarah-Emily Carle: Source: Approved Gate 1 Deck
Note on D91: Sarah-Emily Carle: Source: Gate 3 PMP section 2.1.2 Scope Boundaries
Note on D92: Sarah-Emily Carle: Source: Gate 3 PMP section 2.1.2 Scope Boundaries
Note on D93: Sarah-Emily Carle: Source: Gate 3 PMP section 2.1.2 Scope Boundaries
Note on D94: Sarah-Emily Carle: Source: Gate 3 PMP section 2.1.2 Scope Boundaries
Note on D95: Sarah-Emily Carle: Source: Gate 3 PMP section 2.1.2 Scope Boundaries
Note on D96: Sarah-Emily Carle: Source: Gate 3 PMP section 2.1.2 Scope Boundaries
Note on D97: Sarah-Emily Carle: Source: Gate 3 PMP section 2.1.2 Scope Boundaries
Note on D98: Source: Gate 3 package PMP section 2.1.2
Note on D99: Source: Gate 3 package PMP section 2.1.2
Note on D100: Source: Gate 3 package PMP section 2.1.2
Note on D101: Source: Gate 3 package PMP section 2.1.2
Note on D102: Source: Gate 3 package PMP section 2.1.2
Note on D103: Source: Gate 3 package PMP section 2.1.2
Note on D104: Source: Gate 3 package PMP section 2.1.2

## Budget
Budget Source
SAP
Dashboard
Gating Deck
IP | Project Name | Directorate | Approved Budget | Forecasted Total Expenditures | Variance / Remaining budget | Expenditures to date (2018-19) | Project months to date | Burn Rate/month | Months remaining on project | projected spending until project close-out | Variance between remaining approved budget projected spending | Projet Authority 2016-17 | Project Expenditures 2016-17 | Projet Authority 2017-18 | Project Forecasted Expenditures 2017-18 | Projet Authority 2018-19 | Project Expenditures 2018-19 | Projet Authority 2019-20 | Project Forecasted Expenditures 2019-20 | Projet Authority 2020-21 | Project Forcasted Expenditures 2020-21 | Projet Authority 2021-22 | Project Forcasted Expenditures 2021-22 | Projet Authority 2022-23 | Project Forcasted Expenditures 2022-23 | Budget Risks/Issues/Comments | Budget Health
346 | Food Modernization | FD | 3237100 | 2210860 | 1026240 | 2210860 | 34 | 65025.2941 | 2 | 130050.5882 | 896189.4118 | 1085000 | 928257 | 1270000 | 228396 | 882100 | 1054207 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Incorrect time tracking for FY16/17 and FY17/18 SAP Commitments 2018/19: $155,367 can be de-committed for Manuel Cisneros (TA 4500381752) | Yellow
400 | Common Submission Intake | RMOD | 14826491 | 12975572 | 1850919 | 8635707 |  | unknown |  | #VALUE! | #VALUE! | 2150168 | 2164337 | 3174072 | 2776498 | 5162386 | 3694872 | 4339865 | 4339865 | n/a | n/a | n/a | n/a | n/a | n/a | 1 Source: SAP IO Free Balance Report IP100004000 and IP400004000 run on 2018-12-11 2 Financials now reflect the sum of business and IMSD values | Green
618 | Modernization of Canada Vigilance | MHPD | 2382549 | 2288399 | 94150 | 1814228 | 19 | 95485.6842 | 5 | 477428.4211 | -383278.4211 | n/a | n/a | 94150 | 0 | 1855295 | 1814228 | 433104 | 433104 | n/a | n/a | n/a | n/a | n/a | n/a | No budget or expense in SAP for HPFB/No IO # for CSB MHPD has a P2P ~$1.73 for procurement need to confirm what code and year it is against There is a gap as the commitment for TA beyond December is not in SAP | Green
450 | Drug and Health Product Register R.2 | RMOD | 2250000 | 2240322 | 9678 | 2240322 | 36 | 62231.1667 | 24 | 1493548 | -1483870 | 1310000 | 1105877 | 705000 | 847720 | 235000 | 286725 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Project In Closeout Financial summary now reflects sum of HPFB and IMSD costs | N/A
501 | NNHPD IT Renewal | NNHPD | 5151841 | 4146324 | 1005517 | 4146324 | 23 | 180274.9565 | 6 | 1081649.7391 | -76132.7391 | 411296 | 182991 | 1109903 | 745853 | 3217480 | 3217480 | 413162 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | Revised costing as per Re-Gate 3 package that was sent to ECFIPT July 29, 2018 Need to confirm what funding source will be used for Capitalization amount | Green | project duration 3.33 years
603 | Special Access Program Modernization (eSAP) | TPD | 2666439 | 2666439 | 0 | 633430 | 16 | 39589.375 | 12 | 475072.5 | -475072.5 | n/a | n/a | 204423 | 204423 | 429007 | 429007 | 2033009 | 2033009 | n/a | n/a | n/a | n/a | n/a | n/a | unknown | Green
601 | Revision of Canada's Food Guide | ONPP | 2357299 | 1205000 | 1152299 | 797000 | 12 | 66416.6667 | 6 | 398500 | 753799 | n/a | n/a | 0 | 186000 | 1162794 | 611000 | 828199 | 264000 | 366306 | 144000 | 0 | 17200 | 0 | 17200 | Both the one-time and ongoing project costs for services required by the Government of Canada to publish, maintain, and support the CFG Web Application are being reassessed as the design and technical requirements for the Application are further defined by working with the vendor. A contract amendment with Cistel has been processed and requires additional monies as a result of the new work added (i.e. POR of new CFG visual concepts and Brand) to the project. This results in an increase of $157,400 for FY2018/19. This is a difference of 6.7% of total project authority cost. Breakdown is: +$10,000 and +$259,000 for professional service contract amendments, - $60,000 for maintenance and support due to delayed release by 5 months, and Reallocation of $17,200/yr of enhancement money to FY2017/18 from FY2019/20 and FY2020/21. Actual Cost Expenditures for Branch A-Base funding are not included in the above chart. The amount submitted for the period end Monthly Variance Report will be added once they have been received. | Yellow
602 | Structured Regulatory Documents | RMOD | 2000000 | 1800000 | 200000 | 600000 | 12 | 50000 | 36 | 1800000 | -1600000 | n/a | n/a | n/a | n/a | 600000 | 600000 | 1200000 | 1200000 | 200000 | 0 | n/a | n/a | n/a | n/a | Actual and commitments now reflect the sum of both HPFB and IMSD costs | Green
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | 638064 | 664950 | -26886 | 664950 | 19 | 34997.3684 | 1 | 34997.3684 | -61883.3684 | n/a | n/a | n/a | n/a | 638064 | 664950 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | unknown | Green
634 | Medical Device Post-Market System Renewal | MHPD | 2165051 | 2165051 | 0 | 978333 | 11 | 88939.3636 | 19 | 1689847.9091 | -1689847.9091 | n/a | n/a | 47865 | 47865 | 930468 | 930468 | 1186718 | 1186718 | n/a | n/a | n/a | n/a | n/a | n/a | unknown | Green
703 | Data Analytics Tool | MHPD | 842000 | 842000 | 0 | 805000 | 8 | 100625 | 5 | 503125 | -503125 | n/a | n/a | n/a | n/a | 805000 | 805000 | 37000 | 37000 | n/a | n/a | n/a | n/a | n/a | n/a | unknown | Green
Note on M5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on N5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on O5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on P5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on Q5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on R5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on S5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on T5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on U5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on V5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on W5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on X5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on Y5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on Z5: Sarah-Emily Carle: Source: Dec 2018 Dashboards
Note on A6: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on H6: Sarah-Emily Carle: Project Start date June 2015 - March 2019 (due to forecasting expenditures by fiscal year)
Note on I6: Sarah-Emily Carle: calculated:expenditures to date (2018-19) / Project months to date
Note on J6: Sarah-Emily Carle: Estimate from PM for parts A & B. This may change. April 2019 (due to breakdown in actuals and forecasted expenditures to date) - May 2019
Note on L6: Sarah-Emily Carle: calculated: variance/remaining budget - projected spending utnil project closeout
Note on A7: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on H7: Sarah-Emily Carle: Project Start date June 2015 - March 2018 (due to forecasting expenditures by fiscal year)
Note on I7: Sarah-Emily Carle: calculated:expenditures to date (2018-19) / Project months to date
Note on J7: Sarah-Emily Carle: April 2019 (due to breakdown in actuals and forecasted expenditures to date) - xxxx
Note on A8: Sarah-Emily Carle: Source: Dec. 2018 Dashboard + confirmed against gate 3 PMP
Note on H8: Sarah-Emily Carle: Project start date Oct. 2017 - March 2019 (due to forecasting expenditures by fiscal year)
Note on I8: Sarah-Emily Carle: calculated:expenditures to date (2018-19) / Project months to date
Note on J8: Sarah-Emily Carle: April 2019 (due to breakdown in actuals and forecasted expenditures to date) - Aug 2019
Note on A9: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on H9: Sarah-Emily Carle: Project Start date April 2016 - March 2019 (due to forecasting expenditures by fiscal year)
Note on I9: Sarah-Emily Carle: calculated:expenditures to date (2018-19) / Project months to date
Note on A10: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on H10: Sarah-Emily Carle: Project Start date April 2016 - March 2019 (due to forecasting expenditures by fiscal year)
Note on I10: Sarah-Emily Carle: calculated:expenditures to date (2018-19) / Project months to date
Note on J10: Sarah-Emily Carle: April 2019 (due to breakdown in actuals and forecasted expenditures to date) - Sept 2019
Note on K10: Sarah-Emily Carle:
Note on A11: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on H11: Sarah-Emily Carle: Project Start date Nov. 2017 - March 2019 (due to forecasting expenditures by fiscal year)
Note on I11: Sarah-Emily Carle: calculated:expenditures to date (2018-19) / Project months to date
Note on J11: Sarah-Emily Carle: April 2019 (due to breakdown in actuals and forecasted expenditures to date) - March 2020
Note on A12: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on H12: Sarah-Emily Carle: Project Start date March 2017 - March 2019 (due to forecasting expenditures by fiscal year)
Note on I12: Sarah-Emily Carle: calculated:expenditures to date (2018-19) / Project months to date
Note on J12: Sarah-Emily Carle: April 2019 (due to breakdown in actuals and forecasted expenditures to date) - Sept. 2019
Note on A13: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on H13: Sarah-Emily Carle: Project Start date March 2018 - March 219 (due to forecasting expenditures by fiscal year)
Note on I13: Sarah-Emily Carle: calculated:expenditures to date (2018-19) / Project months to date
Note on J13: Sarah-Emily Carle: April 2019 (due to breakdown in actuals and forecasted expenditures to date) - Mar. 2022
Note on A14: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on H14: Sarah-Emily Carle: Project Start date Sept. 2017 - March 2019 (due to forecasting expenditures by fiscal year)
Note on I14: Sarah-Emily Carle: calculated:expenditures to date (2018-19) / Project months to date
Note on J14: Sarah-Emily Carle: April 2019 (due to breakdown in actuals and forecasted expenditures to date) - April 2019 per project end date
Note on A15: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on H15: Sarah-Emily Carle: Project Start date April 2018 - March 2019 (due to forecasting expenditures by fiscal year)
Note on I15: Sarah-Emily Carle: calculated:expenditures to date (2018-19) / Project months to date
Note on J15: Sarah-Emily Carle: April 2019 (due to breakdown in actuals and forecasted expenditures to date) - Oct. 2020
Note on A16: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on H16: Sarah-Emily Carle: Project Start date Aug. 2018 - March 2019 (due to forecasting expenditures by fiscal year)
Note on I16: Sarah-Emily Carle: calculated:expenditures to date (2018-19) / Project months to date
Note on J16: Sarah-Emily Carle: April 2019 (due to breakdown in actuals and forecasted expenditures to date) - Aug. 2019

## Schedule
Schedule
PMP?
IP | Project Name | Directorate | Major Milestone | Approved (baseline) finish date | Actual / Forecasted Finish Date | Schedule Risks/Issues/ Comments
346 | Food Modernization | FD | Project Start Date | 2015-06-01 | 2015-08-01 | unknown
346 | Food Modernization | FD | Go Live - Iteration 1: Sodium Monitoring Capability | 2016-09-01 | 2016-07-01 | unknown
346 | Food Modernization | FD | Go Live - Iteration 2: CFG Classification Capability | 2017-02-01 | 2017-02-01 | unknown
346 | Food Modernization | FD | Go Live - Iteration 3: Full FCDR | 2018-02-01 | 2018-03-01 | unknown
346 | Food Modernization | FD | Project end date |  |  | unknown
400 | Common Submission Intake | RMOD | Project Start Date | 2016-03-01 |  | unknown
400 | Common Submission Intake | RMOD | Go Live - Common Tracking System | 2020-03-01 | 2020-03-01 | unknown
400 | Common Submission Intake | RMOD | Project End Date | 2020-03-01 | 2020-03-01 | unknown
618 | Modernization of Canada Vigilance | MHPD | Project Start Date | 2017-10-02 | 2017-10-02 | unknown
618 | Modernization of Canada Vigilance | MHPD | CGI publication of Mandatory Reporting Regulations | 2018-06-01 | 2018-06-01 | unknown
618 | Modernization of Canada Vigilance | MHPD | Complete procurement (software and professional services) | 2018-06-01 | 2018-06-01 | unknown
618 | Modernization of Canada Vigilance | MHPD | Confirm configuration and requirements for I&T and ARISg/ESM testing and access to ArisGlobal environment for testing of modules (I&T and ARISg/ESM testing) | 2018-08-10 | 2018-08-10 | unknown
618 | Modernization of Canada Vigilance | MHPD | Produce test summary report of modules from ArisGlobal environment (user acceptance, configuration and automation) | 2018-11-01 | 2018-11-01 | unknown
618 | Modernization of Canada Vigilance | MHPD | Install modules (ARISg I&T v7.x and ARISg/ESM v7.3.x) in SSC environment | 2018-02-04 | 2018-02-04 | unknown
618 | Modernization of Canada Vigilance | MHPD | Pre-UAT signoff - Produce test summary report of modules from SSC environment (user acceptance, configuration and automation) | 2019-03-22 | 2019-03-22 | unknown
618 | Modernization of Canada Vigilance | MHPD | Health Canada CATE signoff for (I&T v7.5 and ARISg/ESM v7.5.) | 2019-04-01 | 2019-04-01 | unknown
618 | Modernization of Canada Vigilance | MHPD | ECFIPT Gate 4 Approval for IP618 | 2019-04-22 | 2019-04-22 | unknown
618 | Modernization of Canada Vigilance | MHPD | Complete Recertification of Trading Partners | 2019-06-13 | 2019-06-13 | unknown
618 | Modernization of Canada Vigilance | MHPD | Go live - Deploy modules (I&T v7.5 and ARISg/ESM v7.5.) to production | 2019-06-17 | 2019-06-17 | unknown
618 | Modernization of Canada Vigilance | MHPD | Project End Date | 2019-08-27 | 2019-08-27 | unknown
450 | Drug and Health Product Register R.2 | RMOD | Project Start Date | 2017-01-09 | 2017-01-09 | unknown
450 | Drug and Health Product Register R.2 | RMOD | Publish API’s | 2017-10-31 | 2017-10-31 | unknown
450 | Drug and Health Product Register R.2 | RMOD | Finalize voluntary adverse event report output | 2017-10-31 | 2017-10-31 | unknown
450 | Drug and Health Product Register R.2 | RMOD | SPM OID Catalogue Database (Controlled Vocabulary Database) | 2018-03-30 | 2018-03-30 | unknown
450 | Drug and Health Product Register R.2 | RMOD | Process to publish SPM to the DHPR | 2018-03-30 | 2018-03-30 | unknown
450 | Drug and Health Product Register R.2 | RMOD | SPM Technical Implementation Package | 2018-03-30 | 2018-03-30 | unknown
450 | Drug and Health Product Register R.2 | RMOD | Go Live - All API’s in production AE Form in production after overcoming technical issues | 2018-10-01 | 2018-10-01 | unknown
450 | Drug and Health Product Register R.2 | RMOD | Project End Date | 2018-04-02 | 2019-02-01 | unknown
501 | NNHPD IT Renewal | NNHPD | Project Start Date | 2016-04-01 | 2016-04-01 | unknown
501 | NNHPD IT Renewal | NNHPD | A&N Tool Implementation – Primary Release | 2018-03-01 | 2018-04-01 | unknown
501 | NNHPD IT Renewal | NNHPD | ePLA Transition to Web Forms | 2018-09-01 | 2018-11-01 | unknown
501 | NNHPD IT Renewal | NNHPD | A&N Tool Implementation – pFix | 2018-10-01 | 2018-10-01 | unknown
501 | NNHPD IT Renewal | NNHPD | Validation Object Model | 2019-07-01 | 2019-09-01 | unknown
501 | NNHPD IT Renewal | NNHPD | Go live - Production Date validation, ePLA and A&N forms and validation database | 2019-07-01 | 2019-09-01 | unknown
501 | NNHPD IT Renewal | NNHPD | Project End Date | 2019-09-01 | 2019-11-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Project Start Date | 2017-11-01 | 2017-11-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Options Analysis (OA) | 2018-08-01 | 2018-08-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Gate 2 Approval | 2018-10-01 | 2018-10-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Complete Cost Estimates | 2017-11-01 | 2017-11-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Gate 3 Approval | 2019-01-01 | 2019-01-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Develop security strategy | 2018-12-01 | 2018-12-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Procuremnt vehicle in place of BPM resources | 2019-03-01 | 2019-03-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Develop integration requirements | 2019-03-01 | 2019-03-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | PIA completion | 2019-03-01 | 2019-03-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Develop migration strategy | 2019-03-01 | 2019-03-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Procurement of Appian licenses | 2019-04-01 | 2019-04-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Business process elaboration, and prototyping complete | 2019-06-01 | 2019-06-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | CGII publication of new regulations | 2019-07-01 | 2019-07-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Threat Risk Assessment (TRA) completion | 2019-08-01 | 2019-08-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Pilot with test group complete (external stakeholders using anonymized data) | 2019-08-01 | 2019-08-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Production environment availability | 2019-08-01 | 2019-08-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Data Migration Complete | 2019-09-01 | 2019-09-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Go Live | 2019-09-01 | 2019-09-01 | unknown
603 | Special Access Program Modernization (eSAP) | TPD | Project End Date | 2020-03-01 | 2020-03-01 | unknown
601 | Revision of Canada's Food Guide | ONPP | Project Start Date | 2017-05-01 | 2017-05-01 | unknown
601 | Revision of Canada's Food Guide | ONPP | Request for Proposal (RFP) Published | 2017-08-01 | 2017-08-01 | unknown
601 | Revision of Canada's Food Guide | ONPP | RFP Awarded | 2017-10-01 | 2017-10-01 | unknown
601 | Revision of Canada's Food Guide | ONPP | Go Live Release 1 - CFG initial mobile-first integrated Web Portal | 2018-11-01 | 2019-01-01 | unknown
601 | Revision of Canada's Food Guide | ONPP | Go Live Release 2 - Enhanced mobile-first integrated Web Portal | 2019-06-01 | 2019-06-01 | unknown
601 | Revision of Canada's Food Guide | ONPP | Project End Date | 2019-09-01 | 2019-09-01 | unknown
602 | Structured Regulatory Documents | RMOD | Project Start Date | 2018-03-01 | 2018-03-01 | unknown
602 | Structured Regulatory Documents | RMOD | Go Live |  |  | unknown
602 | Structured Regulatory Documents | RMOD | Project End Date | 2022-03-01 | 2022-03-01 | unknown
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | Project Start Date | 2017-09-01 | 2017-09-01 | unknown
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | Go Live - Realease 1: Public Interface | 2018-10-01 | 2018-10-01 | unknown
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | Go Live - Realease 2: Workflow Tracker | 2019-03-01 | 2019-03-01 | unknown
627 | IT Enablement of Public Release of Clinical Information (PRCI) | RMOD | Project End Date | 2019-04-01 | 2019-04-01 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Project Start Date | 2018-04-01 | 2018-04-01 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | CGI publication of Mandatory Reporting Regulations | 2018-06-30 | 2018-06-30 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Complete Procurement | 2019-04-17 | 2019-04-17 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Release 1 - Validation of requirements with Vendor | 2019-04-24 | 2019-04-24 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Release 1 - Configuration and Development | 2019-06-19 | 2019-06-19 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | CGII publication of Mandatory Reporting Regulations | 2019-06-30 | 2019-06-30 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Release 1 - Testing in vendor cloud environment Deploy of ArisG 7.5.X to Sandbox environment: confirm configuration and requirements are met; validation of documentation for SSC deployment | 2019-07-22 | 2019-07-22 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Release 1 - Testing in HC environment Produce testing summary reports, install modules in SSC environment | 2019-09-19 | 2019-09-19 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Release 1 - ECFIPT Gate 4 Approval for Release 1 | 2019-10-16 | 2019-10-16 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Go Live - Release 1 - Migration/Deployment | 2019-11-01 | 2019-11-01 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Release 1 - Customer Support handover; Completed ISR | 2019-12-20 | 2019-12-20 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Release 2 - Validation of requirements with Vendor | 2019-04-24 | 2019-04-24 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Release 2 - Configuration and Development | 2019-11-29 | 2019-11-29 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Release 2 - Testing in vendor cloud environment | 2019-12-27 | 2019-12-27 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Release 2 - Testing in HC environment | 2020-02-28 | 2020-02-28 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Go Live - Release 2 - Migration/Deployment | 2020-03-16 | 2020-03-16 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Release 2 - Customer Support handover; Completed ISR | 2020-04-17 | 2020-04-17 | unknown
634 | Medical Device Post-Market System Renewal | MHPD | Project End Date | 2020-10-01 | 2020-10-01 | unknown
703 | Data Analytics Tool | MHPD | Project Start Date | 2018-08-01 | 2018-08-01 | unknown
703 | Data Analytics Tool | MHPD | Gate 3 Approval | 2019-04-01 | 2019-04-01 | unknown
703 | Data Analytics Tool | MHPD | Go Live |  |  | unknown
703 | Data Analytics Tool | MHPD | Project End Date | 2019-08-01 | 2019-08-01 | unknown
Note on A4: Sarah-Emily Carle: Source: Gate 2 Approved Project Charter (V5) Y:\HC\HPFB\_Common - Commun\HPFB Project Management Framework\1 - PPMO\0 - Reference\IP#346 - Food Modernization\Gate 2
Note on D4: Sarah-Emily Carle: Gate 1 authority
Note on E4: Sarah-Emily Carle: Source: Dec. 2018 dashboard
Note on A5: Sarah-Emily Carle: Source: Gate 2 Approved Project Charter (V5) Y:\HC\HPFB\_Common - Commun\HPFB Project Management Framework\1 - PPMO\0 - Reference\IP#346 - Food Modernization\Gate 2
Note on A6: Sarah-Emily Carle: Source: Gate 2 Approved DG-IP v21 deck
Note on A7: Sarah-Emily Carle: Source: Gate 2 Approved DG-IP v21 deck
Note on A8: Sarah-Emily Carle: Source: Gate 2 Approved DG-IP v21 deck
Note on D8: Sarah-Emily Carle: EC-FIPT Gate 5 approval
Note on E8: Sarah-Emily Carle: Source: Dec. 2018 dashboard
Note on D11: Sarah-Emily Carle: EC-FIPT Gate 5 approval
Note on A12: Sarah-Emily Carle: Source: Gate 3 Deck Presentation
Note on D12: Sarah-Emily Carle: Gate 1 authority
Note on A13: Sarah-Emily Carle: Source: Gate 3 Deck Presentation
Note on A14: Sarah-Emily Carle: Source: Gate 3 Deck Presentation
Note on A15: Sarah-Emily Carle: Source: Gate 3 Deck Presentation
Note on A16: Sarah-Emily Carle: Source: Gate 3 Deck Presentation
Note on A17: Sarah-Emily Carle: Source: Gate 3 Deck Presentation
Note on A18: Sarah-Emily Carle: Source: Gate 3 Deck Presentation
Note on A19: Sarah-Emily Carle: Source: Gate 3 Deck Presentation
Note on A20: Sarah-Emily Carle: Source: Gate 3 Deck Presentation
Note on A21: Sarah-Emily Carle: Source: Gate 3 Deck Presentation
Note on A22: Sarah-Emily Carle: Source: Gate 3 Deck Presentation
Note on A23: Sarah-Emily Carle: Source: Gate 3 PMP
Note on D23: Sarah-Emily Carle: EC-FIPT Gate 5 approval
Note on A24: Sarah-Emily Carle: source: PMP Re-gate 3
Note on D24: Sarah-Emily Carle: Gate 1 authority
Note on E24: Sarah-Emily Carle: source: Dec. 2018 dashboard - NOTE this is starting at gate 3 since 106b covered previous gate (old PM framework)
Note on F24: Sarah-Emily Carle: source: Dec. 2018 dashboard - NOTE this is starting at gate 3 since 106b covered previous gate (old PM framework)
Note on A25: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A26: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A27: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A28: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A29: Sarah-Emily Carle: source: PMP Re-gate 3
Note on A30: Sarah-Emily Carle: source: PMP Re-gate 3
Note on E30: Sarah-Emily Carle: source: Gate 5 presentation deck (project timeline slide)
Note on F30: Sarah-Emily Carle: source: Gate 5 presentation deck (project timeline slide)
Note on A31: Sarah-Emily Carle: source: PMP Re-gate 3
Note on D31: Sarah-Emily Carle: EC-FIPT Gate 5 approval
Note on E31: Sarah-Emily Carle: source: Dec. 2108 project dashboard
Note on A32: Sarah-Emily Carle: source: December 2018 dashboar
Note on D32: Sarah-Emily Carle: Gate 1 authority
Note on A33: Sarah-Emily Carle: Source: PMP Section 2.3.2.1
Note on A34: Sarah-Emily Carle: Source: PMP Section 2.3.2.1
Note on A35: Sarah-Emily Carle: Source: PMP Section 2.3.2.1
Note on A36: Sarah-Emily Carle: Source: PMP Section 2.3.2.1
Note on A37: Sarah-Emily Carle: source: December 2018 dashboar
Note on A38: Sarah-Emily Carle: source: December 2018 dashboar
Note on D38: Sarah-Emily Carle: EC-FIPT Gate 5 approval
Note on D39: Sarah-Emily Carle: Gate 1 authority
Note on E39: Sarah-Emily Carle: Source: Gate 2 FIPT approved deck presentation
Note on F39: Sarah-Emily Carle: Source: Gate 2 FIPT approved deck presentation
Note on E40: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F40: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E41: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F41: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E42: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F42: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E43: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F43: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E44: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F44: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E45: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F45: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E46: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F46: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E47: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F47: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E48: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F48: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E49: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F49: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E50: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F50: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E51: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F51: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E52: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F52: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E53: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F53: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E54: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F54: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E55: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F55: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on E56: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F56: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on D57: Sarah-Emily Carle: EC-FIPT Gate 5 approval
Note on E57: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on F57: Sarah-Emily Carle: Source: Gate 3 DG-IP (BEC-DG approved) deck presentation
Note on D58: Sarah-Emily Carle: Gate 1 authority
Note on E58: Sarah-Emily Carle: Source: Dec. 2018 dashboard
Note on E59: Sarah-Emily Carle: Source: PMP Major Milestones
Note on E60: Sarah-Emily Carle: Source: PMP Major Milestones
Note on E61: Sarah-Emily Carle: Source: PMP Major Milestones
Note on E62: Sarah-Emily Carle: Source: PMP Major Milestones
Note on D63: Sarah-Emily Carle: EC-FIPT Gate 5 approval
Note on E63: Sarah-Emily Carle: Source: Dec. 2018 dashboard
Note on F63: Sarah-Emily Carle: Source: Dec. 2018 dashboard
Note on D64: Sarah-Emily Carle: Gate 1 authority
Note on E64: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on F64: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on D66: Sarah-Emily Carle: EC-FIPT Gate 5 approval
Note on E66: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on F66: Sarah-Emily Carle: Source: Dec. 2018 Dashboard
Note on D67: Sarah-Emily Carle: Gate 1 authority
Note on D70: Sarah-Emily Carle: EC-FIPT Gate 5 approval
Note on D71: Sarah-Emily Carle: Gate 1 authority
Note on E71: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F71: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E72: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F72: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E73: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F73: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E74: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F74: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E75: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F75: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E76: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F76: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E77: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F77: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E78: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F78: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E79: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F79: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E80: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F80: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E81: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F81: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E82: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F82: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E83: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F83: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E84: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F84: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E85: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F85: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E86: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F86: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on E87: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F87: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on D88: Sarah-Emily Carle: EC-FIPT Gate 5 approval
Note on E88: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on F88: Sarah-Emily Carle: Source: Gate 3 DG-IP approved deck
Note on D89: Sarah-Emily Carle: Gate 1 authority
Note on D92: Sarah-Emily Carle: EC-FIPT Gate 5 approval

## Overall Project Health
Other Project Data
IP | Project Name | Current Stage | Directorate Lead | Project Objectives | Current Project Status | Overall Project Health
346 | Food Modernization | 4 | FD | IT enablement of the remaining components of the nutritional profile (Canadian Nutrient File, Nutrition Survey System, food and recipe database) to be incorporated into the My Food Guide (MFG) application. | ‒IP346a (Sodium Monitoring Repository Application) and IP346b (Canada Food Guide Classification): The Business Requirement Documentation (BRD) and use cases for both IP346a and IP 346b have been updated. Migration to the cloud completed. ‒ The project team to prepare a critical path and schedule for IP346 A and B confirming target completion dates. It will reflect outstanding requirements and effort estimates to achieve minimum viable product identified in October 2018. The schedule will be presented at the DG Steering Committee on Dec 19. ‒ IP346c: A holistic approach will be taken for Food Component Data Repository (IP346C). A full options analysis, including buy vs build and environment considerations, that builds upon the work already done should be conducted in a timely manner. | Red
400 | Common Submission Intake | 4 | RMOD | Transition to a Common Submission Intake including Regulatory Enrolment, Common Tracking System, docuBridge, Common Electronic Submission Gateway, validation of submission information, and support for international data standards. | Overall Comments - Issues = red due to 400c. Vendor and COTS system cannot meet 1 of the 4 key requirements. See comments below and under Issues section for detail 400a - Regulatory Enrolment Process - Drugs (Pharma/Bio Div 1 & 8 forms): Project team is developing the final production iteration of the XML forms and business process that incorporate all lessons learned to date from the industry pilot and development. - Medical Devices, Veterinary Drugs and Clinical Trials: Project team is developing the XML forms for the upcoming pilots. 400b(i) - Maintenance and Support - Deployment of the next iteration of Automation Phase 9 delayed until February due to business process changes that require more development and vendor (Lorenz) resource availability. - Working with SSC to complete the remaining 3 Business Requirement Documents (BRD) for new environments and environment upgrades. 400b(ii) - Electronic Common Technical Document (eCTD) v4 - Draft Guidance is complete and translated. However, the project team is reconsidering the value in posting the guidance now vs posting in 2020 because eCTD v4 testing is not likely to begin until late 2020. -- The gap between posting the guidance and technical testing is likely to be 1 year to 2 years. -- Other regulators eCTD v4 testing timelines have been slipping. FDA is expected to begin testing late 2019/2020; EMA has deprioritized eCTD v4 testing due to Brexit activity. 400c - Common Tracking System (CTS) - Lorenz confirmed that the CTS will not have the capability to replace the Drug Submission Tracking System (1 of the 4 legacy systems it is meant to replace) until 2021. - Project team adjusted plans to focus on the capabilities that will allow the other 3 legacy systems to be replaced. - Project team is investigating how best to stabilize the Drug Submission Tracking System until it can be replaced. According to Lorenz estimates, that is not likely to be until 2021. | Red
618 | Modernization of Canada Vigilance | 4 | MHPD | Enhance automation activities for the submission and receipt of adverse reaction reports coded in the new version of the International Council on Harmonization (ICH) standard E2B R3 and upgrade the ArisG investment from version of 7.1.4 to 7.3 (2017-18) and 7.4 (2018-19). | - Cost analysis for this contract was conducted and contract approved by PSPC on December 5, 2018. Final contract was sent to vendor on December 6, 2018 for signature. - Continue to update schedule due to delays in finalizing contract with vendor. Reviewed Risk and Issues Register with project team and continue to update accordingly. | Red
450 | Drug and Health Product Register R.2 | 5 | RMOD | Enhancing the availability and usability of regulatory information, such as product monographs and structured product label standards, enhance the ability to search, retrieve and analyze product information, and automate electronic publishing. | Finance IP approved Nov 14, 2018 BEC-DG approved Nov 28, 2018 DG-IP approved Dec 18, 2018 EC-FIPT scheduled for Jan. 7, 2019 | Yellow
501 | NNHPD IT Renewal | 4 | NNHPD | Stabilize the current Natural Health Products Online IT environment with emphasis on Natural Health Products Submission Approval System, Amendment and Notifications (A&N) web forms, and Upgrading the Electronic Product License Application forms. | Phase 1: Replacement of electronic Product Licence (ePLA) and New Amendment Notification Tool (A&N Tool) and analysis of Validation models - ePLA Guidance is now contained within the ePLA form and will be in production with the form in October, 2018 - IP501 WRAP UP Sprint Review Year 1 and Sprint Retrospective Year 1 scheduled for October 15, 2018. - The dependency for the NHPID PFIX to the non-generated monographs was implemented - Business has prioritized the A&N Tool work for development of the next release. - Issue with the signoff of the TRA from security director in the process of reviewing the issues and will escalate to senior management within IMSD. Phase 2: Deployment of a web-based data validation model in conjunction with ePLA - Sprint 3 review and retrospective completed and all data from excel was migrated to an oracle schema, continue to finalize technical stack - Draft Sprint Schedule developed need to run through 4 Sprints to confirm sizing is correct to complete work. - Demo of all the informatica products was given to the team to help support proof of concept. - Working on backlog to support getting the database for the business rules associated to monographs. - Form is fully developed and these fixes and bugs are being addressed in TEST until the CATE environment is ready to support final user acceptance testing. Many of the bugs are related to Web standards. The current production date is Oct 20th; this date may change if the CATE environment is not provisioned by the end of the week. This issue has been escalated to senior management. - As per ECFIPT a Gate 4 check list for the ePLA was created and now with management for approval - All guidance, SOPs, training is underway with business to support the updated ePLA form launch - Deployment plan has been created and all necessary staff understands their role in the plan... Phase 2: Deployment of a web-based data validation model in conjunction with ePLA. Updates to A&N Tool (form) to add new fields | Yellow
603 | Special Access Program Modernization (eSAP) | 3 | TPD | Provision improved electronic intake; communication with physicians and pharmacists; electronic workflow management; capability for electronic signatures related to SAP requests; and block release of drugs that are unavailable for sale in Canada. | Received Treasury Board endorsement to use BPM solution in the Cloud (October 19, 2018) Received EC-FIPT approval for Gate 2 (October 25, 2018) Continued to refine schedule and costs | Yellow
601 | Revision of Canada's Food Guide | 4 | ONPP | Develop a web application that communicates the Government of Canada's evidence-based dietary guidance in a suite of resources to meet the different needs of different users. | • The project is on track to deliver a mobile responsive web application for mid-2019. • The CFG mobile responsive web application IT infrastructure is up and stable; development, testing, and production environment is configured. • Quality assurance and WCAG of web application scheduled for Nov 20-Jan.4th. • System testing (smoke, performance, application load, recovery, stress, functional, and security) scheduled between Dec 10-21st. • Public Opinion Research (POR) for healthy eating pattern was in the field December 10-14th. • All 4 third-party app collaborators are working to integrate CFG content into their apps and are on track to launch post Ministerial launch. • Launch readiness: Cistel will push code into Github for IMSD to push to go live. | Green
602 | Structured Regulatory Documents | 2 | RMOD | Complete production pilots with industry for the structured Product Monograph, CPID and Level III Change Form; i.e., use each regulatory document in live regulatory activities. Update the Drug Product Database Online to include all versions of product monographs for all products; and introduce the capability for it to use the structured product monograph. | - Issue = Yellow due to a dependency on Lorenz resources (expecting shortfalls) and procurement (Business friendly XML editors not currently on the SALSA) - High level business requirement document submitted to IMSD to initiate their formal intake process in readiness for Gate 2. Structured Product Monograph - Draft notice of intent provided to Sr Management for consideration. If approved the notice would be published to the HC website early in 2019. Structured Certified Product Information Document (CPID) - Hosted a bi-lateral meeting with subject matter experts from the US FDA and Health Canada (RMOD, TPD, BGTD) on November 30. Informally agreed to operate collaboratively and have follow-up meetings to discuss pharmaceutical quality - As part of a Proof of Concept, loaded 68 sample CPID's to a machine learning and natural language processing environment for data science analysis (e.g., search, data mining, indexing and AI) Controlled Vocabulary Governance - Worked collaboratively with internal stakeholders (RMOD, TPD, and BGTD) to develop a proposal for Sr Management to consider, including next steps. Standards - Working to develop a multi-lateral relationship with FDA and EMA on the development of an international standard for (1) structured health product labeling and (2) structured pharmaceutical quality information. | Green
627 | IT Enablement of Public Release of Clinical Information (PRCI) | 4 | RMOD | Health Canada is introducing regulations and supporting guidance to permit PRCI in drug submissions, and medical device applications, after Health Canada has made a final regulatory decision. | -Sprint 12: Gate 4 check-in approvals. PRCI public interface - complete medical device integration to PRCI public interface as version 1.3, start QA testing on DEV, prepare release candidate R1.3 for TEST. PRCI work tracking system (WTS), complete the workflow, user permissions, dashboard, and CIP form changes; begin the design sessions for Redactions pages. SSC DEV environment delivered. SSC CITS intake in progress (40d). SSC RA agreement in progress (pending CITS) -Sprint 13: PRCI public interface: R1.3 deploy to HC Cloud TEST, QA and UAT testing and approvals, WCAG testing, CR for IMSD CAB, approval to proceed. Deploy R1.3 to HC Cloud PROD; integrate with CPAB service initiation pages. Ready for Go Live by February 6, 2019. PRCI WTS - complete CIP and time tracking changes, complete Redaction pages designs and start changes. SSC TEST environment in progress. SSC CITS intake approved and SSC RA approved. CITS project activities begin (55d est.) -Sprint 14: PRCI public interface production support. PRCI WTS redaction module, report extracts, search capabilities, finalize French language and WCAG changes. QA and UAT activities on SSC Test environment. Deployment activities for R2 begin, IMSD VA scan, IMSD TRA and SSR activities start (25 days). | Green
634 | Medical Device Post-Market System Renewal | 4 | MHPD | Provide a full review of Medical Device System Renewal options to establish a new path forward for modernizing post-market regulatory activities including post-market report submission intake, work flow management, and publication. | Gate 2 approval granted by EC-FIPT Sept 27, 2018 Recommendation: Remain within HC IT footprint and use the ArisGlobal solution already being used for Canada Vigilance DPMO exemption to proceed with procurement in parallel to Gate 3 governance. CIO request has been submitted and is with MAMD. | Green
703 | Data Analytics Tool | 2 | MHPD | Expand ability to automate through software, the extraction and transformation of adverse reaction (AR) data to potential safety signals using sources from domestic partners and international counterparts. The screening of a large volume of AR data will aim to complement traditional methods of pharmacovigilance such as targeted monitoring strategies. | This project is a 3-Gate Lite, therefore Stage 2 includes both Project Initiation and Project Planning ADM direction is to first look at Aris Global's AG Balance to see if it will meet the requirements as laid out in the HL-BRD | Green

## Rules
Drop-down list
Green
Yellow
Red
Explanation of Status Indicators
Overall Project Health
From the Drop-Down box in cell "P7" Select a status color for the overall project. The interpretation of the color selection is based on the status of the core project management metrics as follows:
Color Status
On scope, on schedule, on budget and managed risks.
Slightly behind schedule or slightly over budget, with some impact on milestones, but corrective actions proposed and with most risks under control.
In serious difficulty and needs immediate attention. Significant intervention required.
■■ | 2 Reds force the overall project health to "RED"
■ | 1 Red force the overall project health to "YELLOW"
■■ | 2 Yellows force the overall project health to "YELLOW"
■■■ | 3 Yellows force the overall project health to "RED"
■■ | 1 Yellow plus 1 Red force the overall project health to "RED"
■■■ | 2 Yellows plus 1 Red force the overall project health to "RED"
■■■■ | Any other combination results in GREEN
Individual Component Metric Status
Cost
Variance of less than 10 %. The project is progressing on track and the intended project outputs are expected to be achieved. Project completion is expected within budget.
Variance of between 10% and 20 %. Some course correction may be required. One or more of the intended project outputs may not be achieved. Project completion may not be possible within budget. Additional funding or re profiling may be required.
Variance of over 20 %. Significant course correction may be required. One or more of the intended project outputs may not be achieved. Project completion may not be possible within the budget. Funding decisions are required.
Schedule
Variance of less than 10 %. The project is progressing on track and the intended project outputs are expected to be achieved. Project completion is expected within the planned schedule
Variance of between 10% and 20 %. Some course correction may be required. One or more of the intended project outputs may not be achieved. Project completion may not be achieved. Project completion may not be possible within the planned schedule.
Variance of over 20 %. Significant course correction may be required. One or more of the intended project outputs may not be achieved. Project completion may not be possible within the planned schedule. Scheduling decisions are required.
Scope
The project is on track. The intended project outputs are expected to be achieved. Identified changes are not expected to negatively impact the project's scope, cost or schedule.
Some course correction may be required. One or more of the intended project outputs may not be achieved. Identified changes may negatively impact the project's scope, cost or schedule and some course correction may be required.
Significant course correction may be required. One or more of the intended project outputs may not be achieved. Identified changes may negatively impact the project's scope, cost or schedule and significant course correction may be required.
Risk
The project is on track. The identified risks are not expected to impact the other project metrics or overall project outputs.
Some course correction may be required. One or more of the intended risks may impact the other project metrics or overall project outputs and some course correction may be required.
Significant course correction may be required. One or more of the intended risks may impact the other project metrics or overall project outputs and significant course correction may be required.
Issues
The project is on track. The project is progressing on track and the intended project outputs are expected to be achieved. All identified issues are manageable within the project's scope, cost and schedule.
Some course correction may be required. One or more of the intended project outputs may not be achieved. One or more of the intended project outputs may not be achieved. One or more of the identified issues are potentially unmanageable within the project's scope, cost or schedule.
Significant course correction may be required. One or more of the intended project outputs may not be achieved. One or more of the identified issues are unmanageable within the project's scope, cost or schedule or the activities undertaken to date to resolve the issue(s) have not been effective.
Individual Risk Classification
Individual Risks - Impact
Minor impact on the project, e.g. < 5% deviation in scope, scheduled end-date or project budget.
Measurable impact on the project, e.g. 5-20% deviation in scope, scheduled end-date or project budget.
Major impact on the project, e.g. >25%% deviation in scope, scheduled end-date or project budget.
Individual Risks - Probability
Unlikely to occur, based on current information, as the circumstances likely to trigger the risk are also unlikely to occur.
Likely to occur as it is clear that the risk will probably materialize.
Highly likely to occur as the circumstances which will cause this risk to materialize are also very likely to be created.
Individual Issue Classification
Individual Issues - Impact
Indicates that issues are under control and well managed. The following are in place, up-to-date and actively managed: - Resolution Plan Target date for resolution; - Ownership identified and accepted, and; - All identified issues are manageable within the scope, cost and schedule baselines.
Indicates caution as issues are not being adequately addressed. One or more of the following might be missing: - Resolution Plan; - Target date for resolution; - Ownership identified and accepted, and; - One or more of the identified issues are potentially unmanageable within the scope, cost or schedule baselines.
Indicates alert, as issues are not being managed, or the resolution activities undertaken to date have not been effective in resolving the issues, and objectives are being impacted – serious attention is required to resolve the issues. One or more of the following is not in place, up-to-date or actively managed: - Resolution Plan; - Target date for resolution; - Ownership identified and accepted, and; - One or more of the identified issues will seriously affect the scope, cost or schedule baselines.